## Project Schedule
PROJECT SCHEDULE TEMPLATE | Unnamed: 1 | Unnamed: 2 | Unnamed: 3 | Unnamed: 4 | Unnamed: 5 | Unnamed: 6
PROJECT NAME | Juan Jose Attias - Quantitative Portfolio Risk Analyzer | Juan Jose Attias | Juan Jose Attias | Juan Jose Attias | Juan Jose Attias | Juan Jose Attias
Create a MySQL-based risk analysis system for financial portfolios | Juan Jose Attias | Juan Jose Attias | Juan Jose Attias | Juan Jose Attias | Juan Jose Attias | Juan Jose Attias
Design a relational database and implement key financial risk metrics (Beta, VaR, Sharpe Ratio) using SQL and Python ETL workflows. | Juan Jose Attias | Juan Jose Attias | Juan Jose Attias | Juan Jose Attias | Juan Jose Attias | Juan Jose Attias
START DATE | END DATE | OVERALL PROGRESS | Juan Jose Attias | Juan Jose Attias | Juan Jose Attias | Juan Jose Attias
00/00/0000 | 00/00/0000 | 0% | Juan Jose Attias | Juan Jose Attias | Juan Jose Attias | Juan Jose Attias
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION (in days) | STATUS | COMMENTS
Set Kickoff Meeting | Alex B. | 2025-01-08 | 2025-01-08 | 2 | Complete | Juan Jose Attias
Agree on Objectives | Frank C. | 2025-09-03 | 2025-09-07 | 5 | Complete | Juan Jose Attias
Detailed Requirements | Jacob S. | 09/07 | 09/12 | 6 | Complete | Juan Jose Attias
Hardware Requirements | Jacob S. | 09/09 | 09/11 | 3 | Overdue | Juan Jose Attias
Final Resource Plan | Jacob S. | 09/11 | 09/15 | 5 | In Progress | Juan Jose Attias
Staffing | Alex B. | 09/16 | 09/17 | 2 | In Progress | Juan Jose Attias
Technical Requirements | Frank C. | 09/17 | 09/21 | 5 | Not Started | Juan Jose Attias
DB Development | Shari W. | 09/22 | 09/24 | 3 | Not Started | Juan Jose Attias
API Development | Shari W. | 09/23 | 09/27 | 5 | Not Started | Juan Jose Attias
UI Client | Alex B. | 09/25 | 09/29 | 5 | Not Started | Juan Jose Attias
Testing | Kennedy K. | 09/24 | 10/02 | 9 | Not Started | Juan Jose Attias
Development Complete | Jacob S. | 10/02 | 10/05 | 4 | Not Started | Juan Jose Attias
Hardware Configuration | Alex B. | 10/05 | 10/07 | 3 | Not Started | Juan Jose Attias
System Testing | Kennedy K. | 10/06 | 10/09 | 4 | Not Started | Juan Jose Attias